## Requirements
ID | Epic | Type | Priority | Status | Title | Goal / User Story | Dependencies | Acceptance Criteria | Verification | Release Gate | Codex Rule | Human Review | Evidence / Blocker
BT-AUD-001 | Audit | Product | P0 | TODO | Create functional MVP gap audit | Inventory current implementation as REAL/PARTIAL/MOCK/HARDCODED/NOT_IMPLEMENTED across core domains. | - | • Audit covers Auth/User/Org/Membership/Activity/Place/AreaPulse/Agent/ResultSet/RSVP/Plans/Notifications/Analytics • Each item links to actual code path or states not implemented • No feature is marked real from UI appearance alone | • Review generated docs/product/FUNCTIONAL-MVP-GAP-ANALYSIS.md | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-RUN-001 | Runtime | Technical | P0 | TODO | Fix physical-device API connectivity and environment config | A physical device can reliably reach the intended development backend. | BT-AUD-001 | • No accidental localhost/127.0.0.1 dependency on physical device • Environment/base URL is explicit • Network/cleartext/HTTPS issues resolved or documented • A real endpoint returns expected response on device | • flutter analyze • physical-device connectivity smoke test | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-RUN-002 | Runtime | Technical | P0 | TODO | Add request tracing and debug diagnostics | Stop guessing when real-device requests fail. | BT-RUN-001 | • requestId is traceable client->server • debug-only panel/log exposes env/auth/last status/result count/error • production build does not expose sensitive diagnostics | • flutter test • go test ./... • debug build smoke | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-DAT-001 | Data | Technical | P0 | TODO | Finalize core schema for Organization Activity Place Participation | Core vertical-slice entities are persisted with stable IDs and constraints. | BT-AUD-001 | • Organization/Membership/Activity/Place/Participation schema exists • Draft/published/cancelled lifecycle represented • Participation uniqueness prevents duplicate RSVP • Migrations are reversible/safe for dev data | • go test ./... • migration applies in dev DB | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-DAT-002 | Data | Technical | P0 | TODO | Create development seed fixtures through real database path | Develop/test with useful Aberdeen data without UI hardcoding. | BT-DAT-001 | • Seed creates sample orgs/activities/places in DB • UI fetches seed via real API • Seed is dev-only and clearly identified | • seed command/script • API returns seeded entities | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-AUT-001 | Auth | Technical | P0 | TODO | Ensure real authentication session reaches backend | Authenticated identity is real and usable for mutations. | BT-RUN-001 | • Login/session works on device • API receives user identity • Logout invalidates client state • Unauthorized mutation is rejected | • flutter test • go test ./... • device login/logout smoke | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-ORG-001 | Organization | Product | P0 | TODO | Implement organization membership and admin authorization | Only authorized organization admins can mutate organization-owned data. | BT-DAT-001, BT-AUT-001 | • Admin role persisted • Backend enforces role • Non-admin receives forbidden • UI does not rely solely on hidden controls | • go test ./... • authorization integration test | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-ACT-001 | Activity Supply | Product | P0 | TODO | Implement Activity create/edit/publish/cancel APIs | Organizations can manage real activities. | BT-ORG-001, BT-DAT-001 | • Create draft • Edit draft/published allowed per policy • Publish makes activity discoverable • Cancel changes state and prevents new RSVP • Validation returns actionable errors | • go test ./... • API integration tests | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-ORG-002 | Organization | Product | P0 | TODO | Build minimal Organization Console activity publisher | Admin publishes without developer/database intervention. | BT-ACT-001 | • Form supports required fields • Place/date/time validation • Draft and publish states visible • Typical event can be published in under 3 minutes after onboarding | • flutter/web tests as applicable • manual publish scenario | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-SRC-001 | Discovery | Product | P0 | TODO | Implement real nearby Activity search | Published activities are retrievable by bounds/time/category. | BT-ACT-001, BT-DAT-002 | • Only published/eligible activities returned • Bounds/time filtering works • Empty is distinct from error • Stable entity IDs returned | • go test ./... • API query tests | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-PUL-001 | Discovery | Product | P0 | TODO | Implement Area Pulse API from real data | Local Pulse reflects the current map/time context. | BT-SRC-001 | • Counts derive from real published data • No hardcoded labels/counts • Zero-data behavior defined • Viewport/time input supported | • go test ./... • API examples for populated/empty areas | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-NOW-001 | Now | Product | P0 | TODO | Connect Now Workspace to real Area Pulse and Activity data | Now is no longer a static shell. | BT-PUL-001, BT-SRC-001, BT-RUN-002 | • Local Pulse is API-driven • Map pins come from real entities • Loading/empty/error states truthful • No hardcoded badminton/current-count demo data | • flutter test • device smoke | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-MAP-001 | Now | Product | P0 | TODO | Stabilize persistent map and keyboard lifecycle | Keyboard and input state never recreate the map or markers. | BT-NOW-001 | • keyboard x20 no visible marker flicker • typing does not clear markers • map controller/key stable • hot paths avoid whole-screen rebuild | • flutter test • real-device keyboard stress | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-MAP-002 | Now | Product | P0 | TODO | Implement stable semantic marker system and selection persistence | Production markers communicate entity type and selection without debug-dot appearance. | BT-MAP-001 | • Activity/Org/Place/Cluster marker support • Stable Entity ID mapping • Incremental marker diff • Selected pin survives camera movement | • widget/integration test • device map interaction | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-MAP-003 | Now | Product | P1 | TODO | Implement explicit Search this area flow | Camera movement changes viewport without destructive automatic search. | BT-MAP-002, BT-SRC-001 | • Move map preserves current ResultSet/selection • CTA appears after settle • New results replace atomically after explicit action • stale request cannot overwrite latest | • flutter tests • device scenario | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-NOW-002 | Now | Product | P1 | TODO | Implement Local Pulse and Active Intent as separate UI models | Users can distinguish area discovery from their active task. | BT-NOW-001, BT-MAP-003 | • Local Pulse appears under top-left control • 2-3 compact items max by default • Active Intent is structured not a long query sentence • movement/collapse behavior implemented | • golden/widget tests • device visual review | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-AGT-001 | Agent | Product | P0 | TODO | Implement normalized MVP intent parser/router | Agent maps supported natural-language tasks to real search operations. | BT-SRC-001, BT-AUT-001 | • Supports find_activity/find_organization/find_place/area_discovery/refine_results/compare_results/create_activity • Slots include time/location/category where applicable • Unknown/unsupported handled explicitly • No fake result generation | • go test ./... • intent test corpus | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-AGT-002 | Agent | Product | P0 | TODO | Implement AgentResponse and ResultSet contract | Conversation answer and structured results share a stable contract. | BT-AGT-001 | • message/resultSet/actions/followUps/mapEffects represented • ResultSet references stable entities • zero result is successful empty not generic failure • request/task IDs available | • go test ./... • contract tests | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-AGT-003 | Agent | Product | P0 | TODO | Connect Now composer to real Agent query flow | User query produces natural-language response + real results + pins. | BT-AGT-002, BT-NOW-001 | • User turn displayed • Agent message precedes result cards • Map syncs same entity IDs • Errors have one owner • + menu not hardcoded to badminton | • flutter tests • device query smoke | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-AGT-004 | Agent | Product | P0 | TODO | Persist conversation task context for follow-ups | Follow-up queries refine current task instead of starting from scratch. | BT-AGT-003 | • Anything closer? reuses prior intent/results • time/category/location context retained • conversation/task IDs stable • context reset action exists | • integration tests • two-turn device scenario | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-NOW-003 | Now | Product | P1 | TODO | Split EntityPeekCard from AgentResultsSheet | Single pin selection stays map-centric while Agent tasks support richer multi-result conversation. | BT-MAP-002, BT-AGT-003 | • Pin -> compact EntityPeekCard • Agent query -> AgentResultsSheet • Sheet detents explicit • long titles resilient | • flutter widget tests • device interaction review | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-RSV-001 | Participation | Product | P0 | TODO | Implement RSVP persistence and Activity detail primary action | A user can truly join/cancel a real activity. | BT-ACT-001, BT-AUT-001 | • Join persists • duplicate join prevented • Cancel updates persistence • cancelled/full activity behavior defined • UI reload reflects server truth | • go test ./... • flutter test • device RSVP + restart | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-PLN-001 | Plans | Product | P0 | TODO | Implement Plans from real participation/save data | Joined activities create retention and remain after restart. | BT-RSV-001 | • Upcoming shows going/pending • Past separates ended activities • server-backed load • restart preserves | • flutter test • device restart scenario | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-SAV-001 | Plans | Product | P1 | TODO | Implement Save independent from RSVP | Users can bookmark without declaring attendance. | BT-AUT-001, BT-ACT-001 | • Save/unsave persists • Plans Saved section reads it • RSVP does not implicitly equal save unless product rule explicitly chosen | • go test ./... • flutter test | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-DET-001 | Activity Detail | Product | P0 | TODO | Complete consumer-grade Activity Detail page | User can confidently decide and act on an activity. | BT-RSV-001 | • Full title/organizer/date/time/place/price/eligibility/description • Join/Save/Share/Navigate states • cancelled/full/loading/error handled • official/source link shown where appropriate | • flutter tests • device content-resilience review | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-NTF-001 | Notifications | Product | P1 | TODO | Implement critical activity notifications | Joined users are informed of important changes. | BT-RSV-001, BT-ACT-001 | • time/venue change notification • cancellation notification • starts-soon reminder mechanism • notification links to activity | • go test ./... • notification integration test | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-INB-001 | Inbox | Product | P1 | TODO | Build Inbox notification center | Users can review operational updates without full stranger messaging. | BT-NTF-001 | • Unread/read state • links to relevant entity • empty/error states • no fake chat features | • flutter test | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-ORG-003 | Organization | Product | P1 | TODO | Build verified Organization profile and public activity list | Users can understand organizer trust/context. | BT-ACT-001 | • Verification state shown truthfully • Upcoming activities • official links • Follow/Ask only if actually supported | • flutter tests • device review | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-OAG-001 | Organization Agent | Product | P1 | TODO | Implement organization verified FAQ knowledge | Organization Agent answers only from verified organization data. | BT-ORG-003, BT-ORG-002 | • Admin can maintain FAQ • Answers cite/derive only from org profile/activities/FAQ • Unknown is explicit • No hallucinated policy/event details | • go test ./... • FAQ scenarios | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-ANA-001 | Analytics | Product | P1 | TODO | Implement pilot funnel analytics | Measure whether Birdtie creates discovery and participation value. | BT-DET-001, BT-RSV-001 | • activity impression/detail/RSVP/save tracked • entry source where feasible • organization sees aggregate basic metrics • no unnecessary sensitive data | • event logging tests • sample pilot report | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-SAF-001 | Safety | Safety | P0 | TODO | Enforce map privacy boundary | Public map never exposes ordinary users' real-time precise location. | BT-MAP-002 | • Map entities limited to permitted public/coarse entities • No precise user tracking endpoint exposed to public flow • docs/tests reflect boundary | • code audit • privacy tests | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Required
BT-SAF-002 | Safety | Safety | P1 | TODO | Add report/support entry points and audit log baseline | Pilot has a minimal incident path. | BT-AUT-001 | • Report entity/action exists or clear support path • Organization/admin mutations are auditable • User-facing support route exists | • go test ./... • UI smoke | Beta | Do not mark DONE until every acceptance item is verified. | Required
BT-PER-001 | Quality | Technical | P0 | TODO | Protect async flows from stale responses | Old search/agent responses never overwrite newer state. | BT-AGT-003, BT-MAP-003 | • request/task/turn identity used • rapid A/B/C query test ends on C • cancel or ignore semantics documented | • automated concurrency test • device rapid-query test | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-PER-002 | Quality | Technical | P1 | TODO | Profile Now hot paths and remove avoidable jank | Consumer-grade map/composer/sheet interaction on target device. | BT-MAP-001, BT-NOW-003 | • no network calls in onCameraMove • no bitmap recreation in hot rebuilds • localized rebuilds • no obvious keyboard/sheet jank | • Flutter performance profile • real-device review | Beta | Do not mark DONE until every acceptance item is verified. | Review
BT-TST-001 | Quality | Technical | P0 | TODO | Create end-to-end vertical-slice integration test/checklist | Prove real Organization->Activity->Discovery->RSVP->Plans flow. | BT-ORG-002, BT-AGT-004, BT-DET-001, BT-PLN-001 | • Admin publish • Student discover • Agent result • Detail • RSVP • Plans • restart persistence all verified | • documented E2E run with PASS/FAIL evidence | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Review
BT-REL-001 | Release | Technical | P0 | TODO | Pass closed-pilot release gate | No known P0 blocker remains before CSSA live event. | BT-TST-001, BT-SAF-001, BT-PER-001, BT-RUN-002 | • flutter analyze/test/build pass • go test/vet pass • P0 backlog zero or explicitly waived by human • support/rollback plan ready • real event data verified | • release checklist | Closed Pilot | Do not mark DONE until every acceptance item is verified. | Required
BT-PIL-001 | Pilot | Operations | P1 | TODO | Prepare CSSA verified profile and one-event pilot | Run smallest truthful partner pilot. | BT-REL-001, BT-ORG-003, BT-ANA-001 | • CSSA confirms profile/event facts • 5-10 testers invited • monitoring owner assigned • feedback/debrief scheduled | • partner confirmation • pilot checklist | Beta | Do not mark DONE until every acceptance item is verified. | Required
BT-PIL-002 | Pilot | Operations | P1 | TODO | Run CSSA pilot and produce post-event learning report | Turn real usage into product decisions and case-study evidence. | BT-PIL-001 | • Funnel captured • student feedback collected • CSSA debrief completed • next iteration decisions documented • no inflated success claims | • pilot report | Beta | Do not mark DONE until every acceptance item is verified. | Required
BT-POL-001 | Polish | Product | P2 | TODO | Finalize visual motion and micro-interaction polish | Polish only after functional reliability is proven. | BT-REL-001 | • Consistent tokens/elevation/motion • No visual polish regresses runtime • Accessibility review | • design QA • device review | Post-Pilot | Do not mark DONE until every acceptance item is verified. | Required

## ExecutionQueue
Queue # | ID | Priority | Epic | Title | Dependencies | Status | Ready? | Next Action
1 | BT-AUD-001 | P0 | Audit | Create functional MVP gap audit | - | TODO | Use taskctl next | python automation/taskctl.py next
2 | BT-RUN-001 | P0 | Runtime | Fix physical-device API connectivity and environment config | BT-AUD-001 | TODO | Use taskctl next | python automation/taskctl.py next
3 | BT-RUN-002 | P0 | Runtime | Add request tracing and debug diagnostics | BT-RUN-001 | TODO | Use taskctl next | python automation/taskctl.py next
4 | BT-DAT-001 | P0 | Data | Finalize core schema for Organization Activity Place Participation | BT-AUD-001 | TODO | Use taskctl next | python automation/taskctl.py next
5 | BT-DAT-002 | P0 | Data | Create development seed fixtures through real database path | BT-DAT-001 | TODO | Use taskctl next | python automation/taskctl.py next
6 | BT-AUT-001 | P0 | Auth | Ensure real authentication session reaches backend | BT-RUN-001 | TODO | Use taskctl next | python automation/taskctl.py next
7 | BT-ORG-001 | P0 | Organization | Implement organization membership and admin authorization | BT-DAT-001, BT-AUT-001 | TODO | Use taskctl next | python automation/taskctl.py next
8 | BT-ACT-001 | P0 | Activity Supply | Implement Activity create/edit/publish/cancel APIs | BT-ORG-001, BT-DAT-001 | TODO | Use taskctl next | python automation/taskctl.py next
9 | BT-ORG-002 | P0 | Organization | Build minimal Organization Console activity publisher | BT-ACT-001 | TODO | Use taskctl next | python automation/taskctl.py next
10 | BT-SRC-001 | P0 | Discovery | Implement real nearby Activity search | BT-ACT-001, BT-DAT-002 | TODO | Use taskctl next | python automation/taskctl.py next
11 | BT-PUL-001 | P0 | Discovery | Implement Area Pulse API from real data | BT-SRC-001 | TODO | Use taskctl next | python automation/taskctl.py next
12 | BT-NOW-001 | P0 | Now | Connect Now Workspace to real Area Pulse and Activity data | BT-PUL-001, BT-SRC-001, BT-RUN-002 | TODO | Use taskctl next | python automation/taskctl.py next
13 | BT-MAP-001 | P0 | Now | Stabilize persistent map and keyboard lifecycle | BT-NOW-001 | TODO | Use taskctl next | python automation/taskctl.py next
14 | BT-MAP-002 | P0 | Now | Implement stable semantic marker system and selection persistence | BT-MAP-001 | TODO | Use taskctl next | python automation/taskctl.py next
15 | BT-MAP-003 | P1 | Now | Implement explicit Search this area flow | BT-MAP-002, BT-SRC-001 | TODO | Use taskctl next | python automation/taskctl.py next
16 | BT-NOW-002 | P1 | Now | Implement Local Pulse and Active Intent as separate UI models | BT-NOW-001, BT-MAP-003 | TODO | Use taskctl next | python automation/taskctl.py next
17 | BT-AGT-001 | P0 | Agent | Implement normalized MVP intent parser/router | BT-SRC-001, BT-AUT-001 | TODO | Use taskctl next | python automation/taskctl.py next
18 | BT-AGT-002 | P0 | Agent | Implement AgentResponse and ResultSet contract | BT-AGT-001 | TODO | Use taskctl next | python automation/taskctl.py next
19 | BT-AGT-003 | P0 | Agent | Connect Now composer to real Agent query flow | BT-AGT-002, BT-NOW-001 | TODO | Use taskctl next | python automation/taskctl.py next
20 | BT-AGT-004 | P0 | Agent | Persist conversation task context for follow-ups | BT-AGT-003 | TODO | Use taskctl next | python automation/taskctl.py next
21 | BT-NOW-003 | P1 | Now | Split EntityPeekCard from AgentResultsSheet | BT-MAP-002, BT-AGT-003 | TODO | Use taskctl next | python automation/taskctl.py next
22 | BT-RSV-001 | P0 | Participation | Implement RSVP persistence and Activity detail primary action | BT-ACT-001, BT-AUT-001 | TODO | Use taskctl next | python automation/taskctl.py next
23 | BT-PLN-001 | P0 | Plans | Implement Plans from real participation/save data | BT-RSV-001 | TODO | Use taskctl next | python automation/taskctl.py next
24 | BT-SAV-001 | P1 | Plans | Implement Save independent from RSVP | BT-AUT-001, BT-ACT-001 | TODO | Use taskctl next | python automation/taskctl.py next
25 | BT-DET-001 | P0 | Activity Detail | Complete consumer-grade Activity Detail page | BT-RSV-001 | TODO | Use taskctl next | python automation/taskctl.py next
26 | BT-NTF-001 | P1 | Notifications | Implement critical activity notifications | BT-RSV-001, BT-ACT-001 | TODO | Use taskctl next | python automation/taskctl.py next
27 | BT-INB-001 | P1 | Inbox | Build Inbox notification center | BT-NTF-001 | TODO | Use taskctl next | python automation/taskctl.py next
28 | BT-ORG-003 | P1 | Organization | Build verified Organization profile and public activity list | BT-ACT-001 | TODO | Use taskctl next | python automation/taskctl.py next
29 | BT-OAG-001 | P1 | Organization Agent | Implement organization verified FAQ knowledge | BT-ORG-003, BT-ORG-002 | TODO | Use taskctl next | python automation/taskctl.py next
30 | BT-ANA-001 | P1 | Analytics | Implement pilot funnel analytics | BT-DET-001, BT-RSV-001 | TODO | Use taskctl next | python automation/taskctl.py next
31 | BT-SAF-001 | P0 | Safety | Enforce map privacy boundary | BT-MAP-002 | TODO | Use taskctl next | python automation/taskctl.py next
32 | BT-SAF-002 | P1 | Safety | Add report/support entry points and audit log baseline | BT-AUT-001 | TODO | Use taskctl next | python automation/taskctl.py next
33 | BT-PER-001 | P0 | Quality | Protect async flows from stale responses | BT-AGT-003, BT-MAP-003 | TODO | Use taskctl next | python automation/taskctl.py next
34 | BT-PER-002 | P1 | Quality | Profile Now hot paths and remove avoidable jank | BT-MAP-001, BT-NOW-003 | TODO | Use taskctl next | python automation/taskctl.py next
35 | BT-TST-001 | P0 | Quality | Create end-to-end vertical-slice integration test/checklist | BT-ORG-002, BT-AGT-004, BT-DET-001, BT-PLN-001 | TODO | Use taskctl next | python automation/taskctl.py next
36 | BT-REL-001 | P0 | Release | Pass closed-pilot release gate | BT-TST-001, BT-SAF-001, BT-PER-001, BT-RUN-002 | TODO | Use taskctl next | python automation/taskctl.py next
37 | BT-PIL-001 | P1 | Pilot | Prepare CSSA verified profile and one-event pilot | BT-REL-001, BT-ORG-003, BT-ANA-001 | TODO | Use taskctl next | python automation/taskctl.py next
38 | BT-PIL-002 | P1 | Pilot | Run CSSA pilot and produce post-event learning report | BT-PIL-001 | TODO | Use taskctl next | python automation/taskctl.py next
39 | BT-POL-001 | P2 | Polish | Finalize visual motion and micro-interaction polish | BT-REL-001 | TODO | Use taskctl next | python automation/taskctl.py next

## Dashboard
Birdtie Functional MVP - TAPD-style Delivery Dashboard
KPI | Value | Stage | Definition | Priority | Count
Total requirements | 39 | UI Prototype | Screens render; not sufficient for MVP | P0 | 25
P0 requirements | 25 | Functional Prototype | Real API + real state | P1 | 13
P1 requirements | 13 | Vertical Slice | Org publish -> Student discover -> RSVP -> Plans | P2 | 1
P2 requirements | 1 | Closed Pilot | Real CSSA event + real testers
Current DONE | 0 | Public Beta | Multi-org reliable growth
North Star Gate
Pilot-ready only when a real Organization Admin can publish a real Activity and a real student can discover it through Now/Personal Agent, open detail, Join/RSVP, and see the persisted participation in Plans without developer intervention.
Execution | Command / Rule
Next task | python automation/taskctl.py next
Start | python automation/taskctl.py start <TASK_ID>
Complete | python automation/taskctl.py done <TASK_ID> --evidence "..."
Block | python automation/taskctl.py block <TASK_ID> --reason "..."
Summary | python automation/taskctl.py summary
Rule | Never use MOCK/HARDCODED success to satisfy a DONE gate.

## ReleaseGates
Gate ID | Gate | Required Before | Checklist | Pass Evidence | Status
G-01 | Runtime connectivity | Functional work | Physical device reaches intended backend; env/base URL explicit; auth visible in diagnostics | Device smoke + logs | TODO
G-02 | Real-data discovery | Vertical slice | Published DB activity returned by nearby search/Area Pulse | API/integration evidence | TODO
G-03 | Agent result integrity | Vertical slice | Agent message + real ResultSet + map entity IDs; follow-up context persists | Two-turn test | TODO
G-04 | Participation persistence | Vertical slice | Join/cancel persists; Plans survives restart | Device restart scenario | TODO
G-05 | Organization self-service | Closed Pilot | Admin can create/edit/publish/cancel without developer intervention | 3-min publish trial | TODO
G-06 | Map runtime | Closed Pilot | Keyboard x20 no flicker; map move preserves selection; stale response protection | Real-device stress | TODO
G-07 | Safety/privacy | Closed Pilot | No public precise user location; support/report path; authz enforced | Audit/tests | TODO
G-08 | Build & tests | Closed Pilot | flutter analyze/test/build + go test/vet pass | Command logs | TODO
G-09 | CSSA event readiness | Live Pilot | Confirmed official facts, monitoring owner, fallback channel, feedback plan | Partner confirmation | TODO

## PilotMetrics
Metric | Definition | Internal Target | Why it matters | Actual | Status
5-min relevance | New user finds >=1 relevant item within 5 minutes | >70% | Tests discovery usefulness
Search -> Detail | Search/agent result leading to detail open | >30% | Tests result relevance
Detail -> Join/Save | Activity detail leading to action | >15% | Tests participation value
7-day return | Tester opens Birdtie again within 7 days | >30% | Early retention signal
Publish time | Typical CSSA activity publish after onboarding | <3 min | Organization operational burden
Partner continuation | Pilot orgs willing to continue | >=3/5 | Supply-side product value
Search/API success | Successful core search/API requests | >98% | Reliability
Map keyboard flicker | Visible marker/map recreation during keyboard stress | 0 | Consumer-grade runtime

## DataDictionary
Entity | Purpose | Key fields / states | Source of truth | MVP?
User | Real human account | id, displayName, profile, preferences | Server DB | Yes
PersonalAgent | User's agent identity/config | userId, preferences/context policy | Server/config | Yes
Organization | Real public organization | id, name, verification, links | Server DB | Yes
OrganizationMembership | Admin/editor permissions | userId, orgId, role | Server DB | Yes
OrganizationAgent | Verified organization Q&A layer | orgId, knowledge policy | Server/config | P1
Activity | Discoverable participation object | status, time, place, category, capacity | Server DB | Yes
ActivityParticipation | RSVP state | userId, activityId, status | Server DB | Yes
Place | Geographic anchor | id, name, lat/lng, address | Server DB/service | Yes
CityContext | Public area context | city/area metadata | Server/service | Yes
Conversation/Turn | Agent dialogue state | conversationId, turns | Server/recoverable | Yes
AgentTask | Normalized user intent | intent, slots, taskId | Server/recoverable | Yes
ResultSet | Structured current results | id, entity refs, context | Server/recoverable | Yes
SavedEntity | Bookmark | userId, entityType, entityId | Server DB | P1
Notification | Operational update | type, target, read state | Server DB | P1
Report/AuditLog | Safety/accountability | actor, action, target, timestamps | Server DB | P1